## Subscription Tasks
Phase | Task ID | Task Description | Status | Assignee | Notes
Phase 1: Subscription Data Modeling | Task 1.1 | Update the user data model to support multi-month upfront subscription packages (Free, Plus, VIP). It needs to securely track package expiration dates, available manual unlock credits, and available AI outbound call credits. Determine the optimal schema and data types for this structure. | Not Started
Phase 2: Premium Subscription UI | Task 2.1 | Build the core Premium Upgrade screen utilizing a top-level toggle between "Self-Service" (Plus) and "Assisted" (VIP) tiers to control the viewable state. | Not Started
Phase 2: Premium Subscription UI | Task 2.2 | Implement the "Self-Service" view. Emphasize the included manual unlock credits and build intuitive UI cards allowing users to select between duration packages (1, 3, 6, 12 months) with their respective bulk pricing. | Not Started
Phase 2: Premium Subscription UI | Task 2.3 | Implement the "Assisted" view. Emphasize the AI Voice Broker features and build the corresponding duration selection cards for the higher-ticket VIP bulk pricing. | Not Started
Phase 3: Stripe Checkout & Backend | Task 3.1 | Build a backend endpoint to dynamically generate Stripe checkout sessions. It must natively handle routing for the high-ticket, multi-month upfront Premium packages based on the user's tier and duration selection. | Not Started
Phase 3: Stripe Checkout & Backend | Task 3.2 | Build a secure, signature-validated webhook listener to process successful server-to-server payment events from Stripe. | Not Started
Phase 3: Stripe Checkout & Backend | Task 3.3 | Implement the backend fulfillment logic upon successful payment. Calculate the user's new subscription expiration date based on the purchased duration block (1, 3, 6, or 12 months), change their active tier status, and allocate the correct amount of manual unlock credits or AI call credits to their profile. | Not Started